Guideline:  Estimating Laws

Caution!  This template was written by a project manager who has been in the project "trenches" for longer than he cares to remember.  (If you haven't guessed, his name is Pete.  Apparently, Pete is still doing project management, against the recommendations of his therapist, he says ().

Introduction from Pete:  The "Estimating Laws" in this file were written in the genre of "shock poetry" to emphatically reinforce some consistently-repeated errors and misunderstandings about human nature and how people's brains work when they are estimating their project schedules.  I originally presented these "Laws" to a group of neophyte project managers and technical leaders during an internal company seminar, to give them some "real world" flavor for this important piece of their new position and spark discussion of this aspect of their jobs.  The laws are not specific to any one project type or area of expertise - the ideas should be useful regardless.

What:  A loosely bound set of Universal Laws that provides the project manager with amusing insight into possible influences on and errors encountered when estimating work on a project. The information is presented with a degree of humor- but important realities are there.

Why:  Estimates are not concrete or absolute or exact.  If they were any of these things, they wouldn’t be called estimates. Unfortunately, those who use our estimates may mis-use them, so aids to getting better estimates and watchfulness for bad influences are a good idea.

There are many ways to estimate things.  Some people making estimates are good at estimating some things and if you are lucky, the things they are good at estimating are the project-related issues in their domain or area of expertise.  Some estimates are based on historical data, sometimes using discrete data.  Many times, the estimates are intuitive.  Many times, the estimates are made with incorrect or, more likely, incomplete data.  Many times estimates are made under pressure to perform or to meet the (optimistic) expectations of management or others.   Many time estimates are made under time duress.  Many times estimates are made with some or all of the above potential problems.

We make estimates we can't get perfect data to predicting cost and time for a project.  If we try to acquire perfect, correct information, we hit a diminishing return phenomenon:     it becomes more and more time consuming to get better and better information.  Usually, costs and time constraints dictate that we do as well as we can, and we move forward with incomplete data and some degree of guessing. The project schedule inevitably contains a degree of information that is incorrect, sometimes a considerable amount of incorrect data.

How: The project manager should repeat these "laws" as a mantra over and over again in their head.  The project manager should mumble them under his or her breath while resisting pressure to reduce the time of the schedule.  The project manager should recite these at the beginning of any project team meeting, particularly during the initiation (early) phases of planning the project, and more passionately as the project leader attempts to get buy-in to the budget and schedule.

Note: The suggested actions in the above paragraph are intended to be humorous.  In the author's view of the world, humor is another prerequisite for successfully completing project after project. (

If you're an experienced project manager mentoring others, these laws can also be used to orient new PMs to this people-centric, uncertain aspect of their job, and open some experience-based knowledge transfer about how to deal with estimating challenges. Be sure to add your own wisdom to the list!

Pete’s Estimating Laws

- Everything takes longer than you think (sometimes a lot longer).

- Thinking about everything takes longer than you think.

- Project Managing and leading a project team is a FULL TIME job, and then some.

- Software Engineers are always optimistic (generally REALLY optimistic).

- Schedules are (almost) always wrong.

- If you under-estimated an early task when you wrote the WBS (schedule), you probably under-estimated middle and later tasks.  Revisit the later phases of the schedule as early as possible when you discover early phase schedule (estimate) errors.

- Business types (upper management) REALLY do use your estimates for planning.  For example, head count, money, customer deliverables, shipping dates, ordering materials, scheduling manufacturing lines, advertising timing, etc.     Be able to express your level of confidence on various estimates when you provide them to others.

- Initially, a good schedule estimate is 80% confidence for near term deliverables, 60-80% for long-term deliverables.  Revisit the schedule and revise your estimates after the Initiation Phase (Kickoff) and again after the Design Phase to improve on these early confidence levels.

- Don’t let yourself be bullied into committing to something you cannot achieve.

- Don’t bully someone else into committing to something they cannot achieve.

- Notify “Need To Know” people AS SOON AS POSSIBLE if there is a significant problem or potential problem in meeting the schedule.  Remember that there was a certain degree of optimism in the schedule originally.  Note:  It's an art to not over-do this.

- Let team members know that you, the project manager, expect early notification of schedule problems as a courtesy.  You decide on the severity or risk of the problem and its impact to the schedule, what actions to take, and what contingencies are appropriate.

- Most people’s estimating skills improve with experience; some don’t.

- Learn your own estimating flaws and compensate for them.  Then learn the flaws in your new estimations and compensate for them.  Repeat continuously while employed as a project manager.

- Learn others' estimating flaws and learn to compensate for them.  Mentor them on improving their flaws and then compensate for their improvements.  Repeat continuously while they are on your project team.

- In some environments, some people are hedging their estimates, some people are expecting them to hedge the estimates and some people are doing neither.  It’s an interesting problem to get all of them to stop this behavior and have people give honest, best-effort estimates.  Laws 14 and 15 are useful for dealing with this variability while you are working to get your team members to be more honest with you.   Laws 13-16 are part of the "people aspects" of the project management job - like it or not, we have to deal with these "real world effects" on the projects we manage.

- Be wary of anyone who wants 100% confidence in an estimate.  90% confidence is an exceptional human achievement for any complex task, even with extremely good data.

- Look up the word “estimate” in the dictionary.  You may find it useful in a meeting.